## GanttChart
[Lập Kế Hoạch] Lịch Trình Dự Án
[CNPM-NC]
| Ngày bắt đầu dự án | 2021-03-22 |  |  |  | Tuần hiển thị | 1 |  | Tuần 1 | [6 empty] | Tuần 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Trưởng nhóm | Nguyễn Văn Chinh | [6 empty] | 2021-03-22 | [6 empty] | 2021-03-29 | [6 empty] | 2021-04-05 | [6 empty] | 2021-04-12 | [6 empty] | 2021-04-19 | [6 empty] | 2021-04-26 | [6 empty] | 2021-05-03 | [6 empty] | 2021-05-10
 | time axis 2021-03-22 to 2021-05-16
WBS | Nhiệm Vụ | LEAD | PREDECESSOR | Ngày bắt đầu | Ngày kết thúc | Ngày | % HT | Ngày làm việc | time axis 2021-03-22 to 2021-05-16
1 | Phân Tích Yêu Cầu |  |  |  | - |  |  | -
1.1 | Mục Tiêu, mục đích chọn đề tài | [Chinh] |  | 2021-03-22 | 2021-03-23 | 2 | 100% | 2
1.2 | Yêu cầu chức năng |  |  | 2021-03-24 | 2021-03-25 | 2 | 100% | 2
1.3 | Yêu cầu phi chức năng |  |  | 2021-03-26 | 2021-03-27 | 2 | 100% | 2
1.4 | Bảng yêu cầu toàn chức năng |  |  | 2021-03-28 | 2021-03-31 | 4 | 100% | 4
1.5 | Bảng trách nhiệm toàn chức năng |  |  | 2021-04-01 | 2021-04-04 | 4 | 100% | 4
2 | Thiết Kế Hệ Thống |  |  |  | - |  |  | -
2.1 | Usecase Diagram |  |  | 2021-04-05 | 2021-04-06 | 2 | 100% | 2
2.2 | Class Diagram |  |  | 2021-04-07 | 2021-04-08 | 2 | 100% | 2
2.3 | Sequence Diagram |  |  | 2021-04-09 | 2021-04-12 | 4 | 100% | 4
2.4 | Sơ đồ quan hệ |  |  | 2021-04-13 | 2021-04-14 | 2 | 100% | 2
2.5 | Sơ đồ tổng quát, DFD 0, DFD 1 |  |  | 2021-04-15 | 2021-04-18 | 4 | 100% | 4
3 | Thiết Kế Giao Diện |  |  |  | - |  |  | -
3.1 | Cấu trúc hệ thống |  |  | 2021-04-19 | 2021-04-22 | 4 | 100% | 4
3.2 | Các giao diện |  |  | 2021-04-23 | 2021-04-25 | 3 | 100% | 3
4 | Nghiệp vụ nâng cao |  |  |  | - |  |  | -
4.1 | Triển khai code |  |  | 2021-04-26 | 2021-05-09 | 14 | 85% | -
4.2 | Thử nghiệm, triển khai hệ thống |  |  | 2021-05-10 | 2021-05-12 | 3 | 0% | -
4.3 | Quản lý cấu hình |  |  | 2021-04-26 | 2021-04-28 | 3 | 100% | 3
4.4 | Quản lý nhân sự |  |  | 2021-04-29 | 2021-05-01 | 3 | 100% | 3
4.5 | Ước lượng chi phí phần mềm |  |  | 2021-05-02 | 2021-05-05 | 4 | 100% | 4
4.6 | Kết luận |  |  | 2021-05-12 | 2021-05-12 | 1 | 0% | -
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.